## Sheet1
Team member | Task Name | Task Type | Start Date | Expcted Delivery Date | Estimated Duration | Describtion and Comments | Status | Reviewer Comments
May Abdelsalam | Write CYRS Document | Non-Technical | 21/1/2020 | 22/1/2020 | 1 day |  | Done
Areej Helal | Write HSI Document | Non-Technical | 22/1/2020 | 23/1/2020 | 1 day |  | Done
Mina Yousry and Bishoy | Write SRS Document | Non-Technical | 22/1/2020 | 23/1/2020 | 1 day |  | Done
Moamen Ahmed | Write RTM | Non-Technical | 23/1/2020 | 24/1/2020 | 1 day |  | Done
May Abdelsalam | Update CYRS Document | Non-Technical | 2020-02-03 | 2020-02-05 | 2 days | update the formating of the CYRS document and update it according to the review document | Reviewed | Req_PO1_DGC_CYRS_009_v1.0 is repeated twice and add reference table
Areej Helal | Update HSI Document | Non-Technical | 2020-02-03 | 2020-02-05 | 2 days | update the formating of the HSI document and update it according to the review document | Done
Bishoy Nabil And Mina Yousry | Update SRS Document | Non-Technical | 2020-02-05 | 2020-02-07 | 2 days | update the formating of the SRS document and modify it to match the updated CYRS document | Done
May Abdelsalam | Update CYRS Document | Non-Technical | 2020-02-06 | 2020-02-07 | 1 day | Update the CYRS document with the review comments and update the formating to match the HSI document | Done
Moamen Ahmed | Update RTM | Non-Technical | 2020-02-07 | 2020-02-07 | 1 hr | update RTM with new CYRS ,SRS ,and HSI requirments | Done
Moamen Ahmed | Review CYRS Document | Non-Technical | 2020-02-06 | 2020-02-06 | 1 hr | Review CYRS document after modifications | Done
Moamen Ahmed | Review HSI Document | Non-Technical | 2020-02-06 | 2020-02-06 | 1 hr | Review HSI document after modifications | Done
Areej Helal | Update Block diagram | Non-Technical | 2020-02-07 | 2020-02-07 | 1 hr | Update Block diagram and use a tool like Proteus to draw the diagram | Done
Bishoy Nabil | Review SRS document | Non-Technical | 2020-02-07 | 2020-02-07 | 1 hr | Review SRS document and make sure it follows the review document and guidlines | Done
Mina Yousry | Minor updates to SRS document | Non-Technical | 2020-02-08 | 2020-02-08 | 10 mins | Remove document status and add status table | Done
Bishoy Nabil And Mina Yousry | Update SRS Document | Non-Technical | 2020-02-18 | 2020-02-20 | 2 days | Update the SRS document according the presentation provided and the SRS review sheet | Reviewed | Split Req_PO1_DGC_SRS_002_v1.1 and Req_PO1_DGC_SRS_003_v1.1 tables Add SRS context diagram Add testing scope ITD or VTD Req_PO1_DGC_SRS_003_v1.1 Req_PO1_DGC_SRS_006_v1.1 Req_PO1_DGC_SRS_009_v1.1 Req_PO1_DGC_SRS_0013_v1.1 Clarify the shall display which data on the LCD Req_PO1_DGC_SRS_0019_v1.1 Remove variable write number instead Req_PO1_DGC_SRS_0020_v1.1 remove cast write display instead Req_PO1_DGC_SRS_0023_v1.1 time is 15 seconds
Bishoy Nabil And Mina Yousry | Update SRS Document | Non-Technical | 2020-02-19 | 2020-02-20 | 1 day | Update SRS document according to previous review | Done
Mina Yousry | Update SRS Document | Non-Technical | 2020-02-25 | 2020-02-26 | 1 day | Update SRS document according to SRS review sheet | Done
May Abdelsalam | Create GDD document and layered architecture | Techinical | 2020-02-25 | 2020-02-27 | 2 days | Initial creation of GDD document and initial layered architecture | Done
Areej Helal | Create APIs for the Application layer | Techinical | 2020-02-25 | 2020-02-27 | 2 days |  | Done
Moamen Ahmed | Create APIs for the HAL layer | Techinical | 2020-02-25 | 2020-02-27 | 2 days |  | Done
Bishoy Nabil | Create APIs for the MCAL layer | Techinical | 2020-02-25 | 2020-02-27 | 2 days |  | Done
Moamen Ahmed | Update GDD requirements | Techinical | 2020-03-02 | 2020-03-02 | 1 day |  | Done
May Abdelsalam | Update input and output signals | Techinical | 2020-03-02 | 2020-03-02 | 1 day |  | Done
Moamen Ahmed | Update GDD requirements | Techinical | 2020-03-03 | 2020-03-04 | 1 day |  | Done
Moamen Ahmed | Update RTM with GDD requirements | Techinical | 2020-03-03 | 2020-03-04 | 1 day |  | Done
Areej Helal | Create CDD for Buzzer | Techinical | 2020-03-03 | 2020-03-05 | 2 days |  | Done
May Abdelsalam | Create CDD for DIO | Techinical | 2020-03-03 | 2020-03-05 | 2 days |  | Done
Bishoy Nabil | Review Buzzer CDD document | Techinical | 2020-03-05 | 2020-03-05 | 1 day |  | Done
Mina Yousry | Review DIO CDD document | Techinical | 2020-03-05 | 2020-03-05 | 1 day |  | Done
Moamen Ahmed | Update GDD docment According to review | Techinical | 2020-03-14 | 2020-03-14 | 1 day |  | Done
Moamen Ahmed | Update buzzer CDD docment According to review | Techinical | 2020-03-14 | 2020-03-14 | 1 day |  | Done
Moamen Ahmed | Update switch CDD docment According to review | Techinical | 2020-03-14 | 2020-03-14 | 1 day |  | Done