## Sheet1
Team member | Task Name | Task Type | Start Date | Expcted Delivery Date | Estimated Duration | Describtion and Comments | Review Status | Reviewer Comments | Status
May Abdelsalam | Write CYRS Document | Non-Technical | 21/1/2020 | 22/1/2020 | 1 day |  |  |  | Done
Areej Helal | Write SRS Document | Non-Technical | 22/1/2020 | 23/1/2020 | 1 day |  |  |  | Done
Mina Yousry and Bishoy | Write HSI Document | Non-Technical | 22/1/2020 | 23/1/2020 | 1 day |  |  |  | Done
Moamen Ahmed | Write RTM | Non-Technical | 23/1/2020 | 24/1/2020 | 1 day |  |  |  | Done
May Abdelsalam | Update CYRS Document | Non-Technical | 2020-02-03 | 2020-02-05 | 2 days | update the formating of the CYRS document and update it according to the review document |  |  | Pending
Areej Helal | Update HSI Document | Non-Technical | 2020-02-03 | 2020-02-05 | 2 days | update the formating of the HSI document and update it according to the review document |  |  | Pending
Bishoy Nabil And Mina Yousry | Update SRS Document | Non-Technical | 2020-02-05 | 2020-02-07 | 2 days | update the formating of the SRS document and modify it to match the updated CYRS document |  |  | Pending
Moamen Ahmed | Update RTM | Non-Technical | 2020-02-07 | 2020-02-07 | 1 hr | update RTM with new CYRS ,SRS ,and HSI requirments |  |  | Pending