## Introduction
Project Name |  |  | Digital Watch
Ref Document |  | CYRS
Ref Version |  | Initial Version
Author |  | Abdelrahman Ali
Last update |  | 31/01/2020
History
Version | Author |  | Date | Change
0.1 | A.Ali |  | 31/01/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
31/01/2020 | A.Ali | Initial Version | CYRS | Page 1 | Status of document must be changed from Draft to Proposed and then Releases after accomplishing cross review on it. | Accepted | Resolved | Mali 7/2/2020: Point is reviewed and closed
31/01/2020 | A.Ali | Initial Version | CYRS | All pages | The version of CYRS document isn’t defined and some pages left blank without any data. | Accepted | Resolved | Mali 7/2/2020: Point is reviewed and closed
31/01/2020 | A.Ali | Initial Version | CYRS | Last page | There is no Reference table for the reference document , even CYRS should have one and the reference is the customer Requirement for the product | Accepted | Resolved | Mali 7/2/2020: Point is reviewed and closed | Accepted
31/01/2020 | A.Ali | Initial Version | CYRS | Document History | Document history has to be at the start & status of document should be draft and after the cross review is done and points fixed then it could be proposed | Accepted | Resolved | Mali 7/2/2020: Point is reviewed and closed | Refused
31/01/2020 | A.Ali | Initial Version | CYRS | List of Figures | List of figures page is blank if you didn’t plan to put data on it you should delete it. | Accepted | Open
31/01/2020 | A.Ali | Initial Version | CYRS | Page 6 & Page 7 | There’s no need to write chapter number (Chapter 1 , 2 , 3) above the section because the scope of CYRS document to explain The system requirements and it isn’t like a book or a novel. | Accepted | Resolved | Mali 7/2/2020: Point is reviewed and closed
31/01/2020 | A.Ali | Initial Version | CYRS | Page 7 | There is no need to define a section for Hardware components in CYRS and instead of that you need to describe The system overview and you could attach a block diagram explains how the system components should work together. | Accepted | Resolved | Mali 7/2/2020: Point is reviewed and closed
31/01/2020 | A.Ali | Initial Version | CYRS | Page 8 | Project History header should be deleted and the points in Software Section should be defined as requirements with a separate requirement ID for each point. | Accepted | Resolved | Mali 7/2/2020: Point is reviewed and closed
31/01/2020 | A.Ali | Initial Version | CYRS | Page 7 | - This point in Software section states that : Digital calculator that can be turned on/o_x000b_ using a button from the keypad. There isn’t a customer specification states that you need to turn on/off the calculator using a button from the keypad. You shouldn’t take a step forward and guess something not mentioned by the customer in CRS until taking customer approval. - Same in this point “The mathematical operation will not be erased after pressing the assignment operation button”. | Accepted | Resolved | Mali 7/2/2020: Point is reviewed and closed
31/01/2020 | A.Ali | Initial Version | CYRS | Features | Should define an appropriate title for the table you used to put a content or data on it to be expressed So, need to change the title of the table defined in Features section. | Accepted | Resolved | Mali 7/2/2020: Point is reviewed and closed, Features section is removed although there is no comment about this in the history
31/01/2020 | A.Ali | Initial Version | CYRS | Features | You need to make your requirement more clarified from the system level prospective. In Req PO1 DGC CYRS 001 v1.0 instead of saying Hardware shall turn the calculator on/o_x000b_ff when the button is pressed. You can say: the calculator shall be turned on / off when a press is triggered using a button connected to the system. | Accepted | Resolved | Mali 7/2/2020: Point is reviewed and closed
31/01/2020 | A.Ali | Initial Version | CYRS | Features | The CYRS req shall not say the software shall do xxxx , as the CYRS descrip the overall system , then SRS will descrip the SW So CYRS shall be more abstracted. So, all Requirements need to be updated with system level prospective not SW prospective | Accepted | Resolved | Mali 7/2/2020: Point is reviewed and closed
Resolved
[9 empty] | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open