## Introduction
Project Name |  |  | Digital Watch
Ref Document |  | HSI
Ref Version |  | Initial Version
Author |  | Abdelrahman Ali
Last update |  | 31/1/2020
History
Version | Author |  | Date | Change
0.1 | Abdelrahman Ali |  | 31/01/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Open point : description of problem | Decision | Status | Comment
2020-07-02 | Ali | Initial Version | Please provide a word document for SRS | Accepted | Resolved | Ali 13/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | Status of document must be changed from Draft to Proposed | Accepted | Resolved | Ali 13/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | There is no Reference table for the reference document | Accepted | Resolved | Ali 13/2/2020: Point is closed | Refused
2020-07-02 | Ali | Initial Version | There’s no need to write chapter number (Chapter 1 , 2 , 3) above the section because it isn’t like a book or a novel. | Accepted | Resolved | Ali 13/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | Please provide a table for every single requirement like the on in the presentation and remove page 4 | Accepted | Resolved | Ali 13/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | Req PO1 DGC SRS 005 v1.0: Don’t display + sign before the operand, no need for that just "- sign" is needed | Accepted | Open | Ali 13/2/2020: Don't display word "sign", I meant "-" sign | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
2020-07-02 | Ali | Initial Version | Clarify that this behavior will be done under condition "if the user pressed = before enter an operation" | Accepted | Open |  | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open
2020-07-02 | Ali | Initial Version | Req PO1 DGC SRS 009 v1.0: Don't say "SW shall not" it should be "SW shall handle division by zero" the customer wanted this ? To not allow division ? Please check SIQ sheet raw 5 and CYRS req: Req_PO1_DGC_CYRS_009_v1.0 | Accepted | Resolved | Ali 13/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | There is no requirement about SW shall read the input from keypad and how to decide the pressed key | Accepted | Open
2020-07-02 | Ali | Initial Version | Req PO1 DGC SRS 0010 v1.0: You should split this requirement to 2 requirements the first one -> to have a different tone for every button the second one -> to output the tones on the buzzer | Accepted | Open
2020-07-02 | Ali | Initial Version | For all display requiremtns: You should clarify the requirement to have: - SW shall send to LCD data: xxx t, and Cursor position: xxx and make a nother requirement for all display requirememnts: - SW shall display on LCD the send data on the sent position | Accepted | Open
2020-07-02 | Ali | 1.3 | No need for requirement SRS_006 | Accepted | Open
2020-07-02 | Ali | 1.3 | Where buzzer requirements gone !! | Accepted | Open
2020-07-02 | Ali | 1.3 | in SRS_001: Don’t say SW shall call function it should be "SW shall check the pressed key" | Accepted | Open
2020-07-02 | Ali | 1.3 | There is no differnce between SRS_001 and SRS_002 they have the same scope "detecting the pressed key" | Accepted | Open