## Introduction
Project Name |  |  | Digital Watch
Ref Document |  | HSI
Ref Version |  | Initial Version
Author |  | Abdelrahman Ali
Last update |  | 31/1/2020
History
Version | Author |  | Date | Change
0.1 | Abdelrahman Ali |  | 31/01/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Open point : description of problem | Decision | Status | Comment
2020-07-02 | Ali | Initial Version | Please provide a word document for SRS | Accepted | Resolved | Ali 13/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | Status of document must be changed from Draft to Proposed | Accepted | Resolved | Ali 13/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | There is no Reference table for the reference document | Accepted | Resolved | Ali 13/2/2020: Point is closed | Refused
2020-07-02 | Ali | Initial Version | There’s no need to write chapter number (Chapter 1 , 2 , 3) above the section because it isn’t like a book or a novel. | Accepted | Resolved | Ali 13/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | Please provide a table for every single requirement like the on in the presentation and remove page 4 | Accepted | Resolved | Ali 13/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | Req PO1 DGC SRS 005 v1.0: Don’t display + sign before the operand, no need for that just "- sign" is needed | Accepted | Resolved | Ali 13/2/2020: Don't display word "sign", I meant "-" sign Ali 19/2/2020: Point is closed | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
2020-07-02 | Ali | Initial Version | Clarify that this behavior will be done under condition "if the user pressed = before enter an operation" | Accepted | Resolved | Ali 19/2/2020: Point is closed | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open
2020-07-02 | Ali | Initial Version | Req PO1 DGC SRS 009 v1.0: Don't say "SW shall not" it should be "SW shall handle division by zero" the customer wanted this ? To not allow division ? Please check SIQ sheet raw 5 and CYRS req: Req_PO1_DGC_CYRS_009_v1.0 | Accepted | Resolved | Ali 13/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | There is no requirement about SW shall read the input from keypad and how to decide the pressed key | Accepted | Resolved | Ali 24/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | Req PO1 DGC SRS 0010 v1.0: You should split this requirement to 2 requirements the first one -> to have a different tone for every button the second one -> to output the tones on the buzzer | Accepted | Resolved | Ali 24/2/2020: Point is closed
2020-07-02 | Ali | Initial Version | For all display requiremtns: You should clarify the requirement to have: - SW shall send to LCD data: xxx t, and Cursor position: xxx and make a nother requirement for all display requirememnts: - SW shall display on LCD the send data on the sent position | Accepted | Resolved | Ali 19/2/2020: Point is closed
2020-07-02 | Ali | 1.3 | No need for requirement SRS_006 | Accepted | Resolved | Ali 19/2/2020: Point is closed
2020-07-02 | Ali | 1.3 | Where buzzer requirements gone !! | Accepted | Resolved
2020-07-02 | Ali | 1.3 | in SRS_001: Don’t say SW shall call function it should be "SW shall check the pressed key" | Accepted | Resolved | Ali 19/2/2020: Point is closed
2020-07-02 | Ali | 1.3 | There is no differnce between SRS_001 and SRS_002 they have the same scope "detecting the pressed key" | Accepted | Resolved | Ali 19/2/2020: Point is closed
19/2/2020 | Ali | 1.3 | In SRS_006 : Inputs shall be "Data, postion" | Accepted | Resolved
19/2/2020 | Ali | 1.3 | There is many requirements contains the same requirement "SW shall display on LCD the send data on the sent position" hust one requirement about LCD is enough | Accepted | Resolved
19/2/2020 | Ali | 1.6 | Unfortunately you took the context diagram copy paste from the slide without adding single line, also with out adding buzzer in the context diagram | Accepted | Resolved
19/2/2020 | Ali | 1.6 | For every output in the context diagram I shall find every output signal in the requirements output field, "LCD" still an putput signal used in the requirements while it shall be replaced with the defined output signals in the context diagram | Accepted | Resolved
19/2/2020 | Ali | 1.6 | Move the context diagram before requirememnts section | Accepted | Resolved