## Introduction
Project Name |  |  | Digital Watch
Ref Document |  | HSI
Ref Version |  | Initial Version
Author |  | Abdelrahman Ali
Last update |  | 31/1/2020
History
Version | Author |  | Date | Change
0.1 | Abdelrahman Ali |  | 13/03/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Open point : description of problem | Decision | Status | Comment
13/3/2020 | Ali | Initial Version | Req_PO1_DGC_CDD_Buzzer_001 V1.0: Input argument shall be "void" | Accepted | Open
13/3/2020 | Ali | Initial Version | Req_PO1_DGC_CDD_Buzzer_002 V1.0: Input argument shall be "void" | Accepted | Open
13/3/2020 | Ali | Initial Version | Req_PO1_DGC_CDD_Buzzer_003 V1.0: - Input argument shall be "void" - There are no different tones for every key they all have the same tone | Accepted | Open
13/3/2020 | Ali | Initial Version | SW context: Move it before APIs section, also it's empty | Accepted | Open
13/3/2020 | Ali | Initial Version | Flow charts are wrong, for ex: BUZZER_SetBuzzerOn flow chart shall have the following steps: 1- start 2- Set buzzer pin to HIGH by calling GPOI_SetPinValue 3- End | Accepted | Open