## Sheet1
Task | Assigned Team Member | Start Date | Delivery date | Notes
Update Project Plan with week 2 | Moamen Ahmed | 2020-02-02 | 2020-02-02
Update CYRS document | May Abdelsalam | 2020-02-03 | 2020-02-06 | Due to technical difficulties it was uploaded a day late
Reviewed CYRS Document | Moamen Ahmed | 2020-02-06 | 2020-02-06
Update HSI document | Areej Helal | 2020-02-03 | 2020-02-05
Reviewed HSI Document | Moamen Ahmed | 2020-02-06 | 2020-02-06
Update CYRS document | May Abdelsalam | 2020-02-06 | 2020-02-06 | Further updates to CYRS according to review comments