## Sheet1
Team member | Task Name | Task Type | Start Date | Deadline | Estimated Duration | Describtion and Comments
May Abdelsalam | Write CYRS Document | Non-Technical | 21/1/2020 | 22/1/2020 | 1 day
Areej Helal | Write SRS Document | Non-Technical | 22/1/2020 | 23/1/2020 | 1 day
Mina Helmy and Bishoy | Write HSI Document | Non-Technical | 22/1/2020 | 23/1/2020 | 1 day
Moamen Ahmed | Write RTM | Non-Technical | 23/1/2020 | 24/1/2020 | 1 day